## Defects
Defect # | Status | Raised By | Tested on Version | TestCase Id | Steps to Reproduce | Expected Results | Actual Results | Priority | Severity
1 | Open | Nitish R | v3 | SM6 | 1) Click on Delete Account 2) Enter required fields 3) Submit | 1) A pop - up "Do you really want to delete this account?" | No confirmation message shown | Low | Low
2 | Open | Nitish R | v3 | SM11 | 1) Click on Delete Customer 2) Enter Customer id 3) Submit | 1) A pop up "Do you really want to delete this customer?" | No confirmation message shown | Low | Low
3 | Open | Nitish R | v3 | SM14 | 1) Click on Edit Customer 2) Enter Customer id 3) Submit | 1)A pop - up "Customer does not exist" 2) Redirect to Delete customer | alert " You are not authorise to edit this account!" redirect to delete customer page | Low | Low
4 | Open | Nitish R | v3 | SM15 | 1) Click on Delete Customer 2) Enter Customer id 3) Submit | 1)A pop - up "Customer does not exist" 2) Redirects to Delete Customer | alert " You are not authorise to delete this account!" redirect to delete customer page | Low | Low
5 | Open | Nitish R | v3 | SM17 | 1) Execute the above test case 2) Refresh Fund Transfer detail page | Page should redirect to fund transfer page | Not redirecting to fund transfer page on clicking refresh button | Low | Low
6 | Open | Nitish R | v3 | SM19 | 1) Click on Fund Transfer 2) Enter all required fields 3) Submit | 1) A pop - up " Account # does not exist" | 1) A pop up "You are not authorize to Transfer Funds from this account!!" | Medium | Low
7 | Open | Nitish R | v3 | SM20 | 1) Cliick on Fund Transfer 2) Enter all required fields 3) Submit | 1) A pop up "You are not authorize to Transfer Funds from this account!!" | 1) A pop up "No details found for this account!!" | Medium | Low
8 | Open | Nitish R | v3 | SM21 | 1) Click on Fund Transfer 2) Enter all required fields 3) Submit | 1) A pop up "Payers account No and Payees account No Must Not be Same!!!" | No pop up and fund transfer sucessful or for non existing customer pop up "No details found for this account!!" is shown | Medium | Low
9 | Open | Nitish R | v3 | SM22 | 1) Click on Fund Transfer 2) Enter all required fields 3) Submit | 1) A pop up "Transfer Failed. Account Balance low!!" | 1) A pop up "You cant transfer your account balance is low" | Medium | Low
10 | Open | Nitish R | v3 | SM25 | 1) Refresh Deposit detail Page | Page should redirect to Deposit Page | Not redirecting to deposit page on clicking refresh button | Medium | Low
11 | Open | Nitish R | v3 | SM28 | 1)Click on Withdrawal 2) Enter all required fields 3) Submit | An Error message "Transaction failed account balance is low !!" | withdrawal done | Medium | Low
12 | Open | Nitish R | v3 | SM32 | 1) Click on Customized statement 2) Enter all required fields 3) Submit | 1) pop - up "From date field should be lower than to date field" | 1) pop - up "No transaction details found" | Medium | Low
13 | Open | Nitish R | v3 | SC5 | 1) Click on Balance enquiry 2) Enter wrong account number which is not associated with customer 3) Submit | Display alert message " You are not authorize to get Balance details of this account!! " | You can see balance of any account | Medium | Low
14 | Open | Nitish R | v3 | SC9 | 1) Refresh Fund Transfer detail Page shown in above test case | Redirect to Fund Transfer input Page | Not redirecting and fund is transfer again | High | Medium
15 | Open | Nitish R | v3 | SC11 | 1) Click on Fund Transfer 2) Enter wrong Payer account number which is not associated with customer 3) Submit | Display alert messsage "You are not authorize to Transfer Funds from this account!! " | Not displaying alert message and transfers the fund successful | High | Medium
16 | Open | Nitish R | v3 | SC12 | 1) Click on Fund Transfer 2) Enter wrong Payer or Payees account number which is not available in database 3) Submit | Display alert messsage " Account ### does not exist!!! " | Display alert messsage " No details found for this accounts !!! " | High | Medium
17 | Open | Nitish R | v3 | SC13 | 1) Click on Fund Transfer 2) Enter same Payer account number and Payees account number which is available in database 3) Submit | Display alert messsage " Payers account No and Payees account No Must Not be Same!!! " | No pop up and fund transfer sucessful or for non existing customer pop up "No details found for this account!!" is shown | High | Medium
18 | Open | Nitish R | v3 | SC14 | 1) Click on Mini Statement 2) Enter all required fields 3) Submit | Display alert messsage " You are not authorize to generate statement of this Account!! " | Ministatement is generated for any account that exists in database | High | Medium
19 | Open | Nitish R | v3 | SC16 | 1) Click on customize statement 2) Enter all required fields 3) Submit | Display alert messsage " You are not authorize to generate statement of this Account!! " | Customized statement is generated for any account that exists in database | High | Medium
20 | Open | Nitish R | v3 | SC18 | 1) Click on customize statement 2) Enter all required fields 3) Submit | Display alert messsage " FromDate field should be lower than ToDate field!!" | Display alert messsage " No details found for this accounts !!! " | High | Medium
| Open | Nitish R | v3 | WS5 | 1) Enter a value in Account Number Field in URL which is exist in database 2) Press Enter | A Success message with mini statement in the json format should be displayed | Json format fail | High | Medium
21 | Open | Nitish R | v3 | WS6 | 1) Do not enter a value in account number in URL | An error in message "No Data " should be displayed in json format | Data is shown | High | Medium